## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
I can play a new sudoku puzzle if I don't want to continue my current | Server-Sudoku Generation | 4 | 0 | 0 | 0 | 0
I can occupy my spare time and have a positive incentive to continue working on my habits | Server-Sudoku Implementation | 4 | 0 | 0 | 0 | 0
I can get hints when I get stuck in the puzzle and have an incentive to achieve more habits | Server-Sudoku Hints | 2 | 2 | 0 | 0 | 0
I can occupy my spare time and have a positive incentive to continue working on my habits | Client-Sudoku Transmission | 2.5 | 2.5
I can get hints when I get stuck in the puzzle and have an incentive to achieve more habits | Client-Sudoku hints | 1.5 | 1.5
I can occupy my spare time and have a positive incentive to continue working on my habits | UI-Sudoku game | 4 | 4 | 1
I can occupy my spare time and have a positive incentive to continue working on my habits | Client-Sudoku Verification | 3 | 0
All of them | Server-Client Integration | 4 | 2
I can occupy my spare time and have a positive incentive to continue working on my habits | Client-Sudoku Game | 6 | 6 | 6
All of them | General Project Clean-up | 2 | 2
All of them | UI-Clean-up | 1 | 1 | 1
| Estimate Totals | 34 | 21 | 8 | 0 | 0