## Sprint Backlog
Task | Associated User Story | Assigned To… | Estimate
Implement being able to add a habit to the habit tracker |  |  | 30 minutes
Implement being able to complete a habit for the day |  |  | 1hour
Implement status of habits for the day |  |  | 1hour
Implement removing habits |  |  | 30 minutes
implement coin rewards for completing habits |  |  | 1hour
Implement login for user |  |  | 1 hour
(Stretch) Implement sudoku generator |  |  | 2 hours
(Stretch) implement saving sudoku progress |  |  | 1 hour
(Stretch) implement sudoku verification |  |  | 2 hours
Total Time To Complete |  |  | 10 hours