## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
I want to be able to create an account | Add registration UI | 4 | 4
I want to be notified when I complete milestones | Milestone Notifications | 6.25 | 6.25
I want to be notified when a habit needs to be done | Reminder Notifications | Unsure * 4
| Rework habit screen UI | 4 | 4
I want to be able to add habits | Server - Add habit | 3 | 3
I want to be able to earn coins for completing a habit | Server - Complete Habits | 2 | 2
I want to be able to earn coins for completing a habit | Server - Grant coins on habit completion | 4 | 4
I want to be able to create an account | Server - Login | 2 | 2
I want to be able to create an account | Server - Register user | 2.5 | 0
I want to be able to remove habits | Server - Remove Habit | 2 | 2
I want to be able to retrieve habits | Server - Retieve habits | 2 | 2
I want to be able to modify habits | Server - Update Habits | 4 | 4
I want to be able to add habits | ServerCommunicator - Add habit | 5 | 5
I want to be able to earn coins for completing a habit | ServerCommunicator - Complete habits | 5 | 5
I want to be able to create an account | ServerCommunicator - Login | 2.5 | 2.5
I want to be able to create an account | ServerCommunicator - Register user | 6 | 6
I want to be able to remove habits | ServerCommunicator - Remove Habit | 5 | 5
I want to be able to retrieve habits | ServerCommunicator - Retrieve habits | 5 | 5
I want to be able to modify habits | ServerCommunicator - Update Habits | 5 | 5
| Estimate Totals | 69.25 | 66.75 | 0 | 0 | 0