## Sheet1
Related User Story | Asignee | Task Description | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
I can play a new sudoku puzzle if I don't want to continue my current | Shawn | Server-Sudoku Generation | 4 | 0 | 0 | 0 | 0
I can occupy my spare time and have a positive incentive to continue working on my habits | Shawn | Server-Sudoku Implementation | 4 | 0 | 0 | 0 | 0
I can get hints when I get stuck in the puzzle and have an incentive to achieve more habits | Shawn | Server-Sudoku Hints | 2 | 2 | 0 | 0 | 0
I can occupy my spare time and have a positive incentive to continue working on my habits | Bryson | Client-Sudoku Transmission | 2.5 | 2.5 | 4 | 0 | 0
I can get hints when I get stuck in the puzzle and have an incentive to achieve more habits | Bryson, Matt | Client-Sudoku hints | 1.5 | 1.5 | 1.5 | 0 | 0
I can occupy my spare time and have a positive incentive to continue working on my habits | Matt | UI-Sudoku game | 4 | 4 | 1 | 0 | 0
I can occupy my spare time and have a positive incentive to continue working on my habits | Matt, Bryson | Client-Sudoku Verification | 3 | 0 | 0 | 0 | 0
All of them | Everyone | Server-Client Integration | 4 | 2 | 1 | 0.5 | 0
I can occupy my spare time and have a positive incentive to continue working on my habits | Matt | Client-Sudoku Game | 6 | 6 | 6 | 5 | 0
All of them | Craig | General Project Clean-up | 2 | 2 | 1 | 0.5 | 0
All of them | Craig | UI-Clean-up | 1 | 1 | 1 | 0.5 | 0
|  | Estimate Totals | 34 | 21 | 15.5 | 6.5 | 0